# ADVANTECH PROJECT - LESSONS LEARNED & CONTINUOUS IMPROVEMENT

Project: Advantech North America Campus
Final Account: $75,483,200
Our Estimate: $64,992,944
Variance: +$10,490,256 (+16.1%)
Date: January 31, 2026

## EXECUTIVE SUMMARY

The Advantech North America Campus project revealed critical gaps in our ACCE-V3 estimation system. While our final estimate was only 13.8% below the actual final account (vs. initial 44.1% underestimation), the analysis identified five root causes that, if addressed, can improve future accuracy to ±5%.

Key Finding: The three most critical factors for accurate estimation are: 1. Confirming prevailing wage status (+$2.3M impact) 2. Adjusting material escalation by schedule (+$2.0M impact) 3. Reserving for change order risk (+$4.3M impact)

## LESSON 1: PREVAILING WAGE CONFIRMATION IS CRITICAL

### What We Missed

We did not confirm whether the Advantech project was subject to prevailing wage requirements.

### Impact

- Cost Impact: +$2.3M-$3.2M (21.9% of total variance)

- Labor Multiplier: Used 1.18x-1.22x (mixed labor) instead of 1.28x-1.35x (prevailing wage)

- Project Impact: For $13.7M AASC hard cost, difference was +$280K

### Root Cause

- We assumed mixed labor rates without confirming prevailing wage status

- We did not ask the GC directly: “Is this project subject to prevailing wage requirements?”

- We did not verify with state/local labor department

### Solution Implemented

New Rule 6 in ACCE-V3 System Instruction: - ALWAYS ask GC: “Is this project subject to prevailing wage requirements?” - If YES: Use 1.28x-1.35x labor multiplier - If NO: Use 1.15x-1.22x labor multiplier - If UNCERTAIN: Use 1.25x as conservative middle ground

### Action Items for Future Projects

- Week 1: Confirm prevailing wage status with GC

- Week 1: Verify with state/local labor department

- Week 1: Adjust labor multiplier accordingly

- Week 2: Recalculate hard cost with correct multiplier

### Evidence from Advantech

- Project location: Tustin, CA (industrial/warehouse)

- Project size: $75.5M (above typical prevailing wage threshold)

- Actual labor multiplier: Likely 1.28x-1.35x (based on final account)

- Our assumption: 1.18x-1.22x

- Lesson: California industrial projects are frequently subject to prevailing wage

## LESSON 2: MATERIAL ESCALATION MUST BE ADJUSTED BY SCHEDULE

### What We Missed

We applied a fixed 7% material escalation factor for a 21-month project, but actual escalation was 10-12%.

### Impact

- Cost Impact: +$2.0M-$3.0M (19.1% of total variance)

- Escalation Applied: 7%

- Escalation Actual: 10-12%

- Key Materials: Structural steel (+20-25%), electrical equipment (+15-20%)

### Root Cause

- We used a fixed 7% escalation without considering project duration

- We did not account for material price volatility during 21-month construction

- We did not apply quarterly adjustments for volatile materials

### Solution Implemented

New Material Escalation Guidelines:

| Project Duration | Escalation Factor | Application |
| --- | --- | --- |
| 6-12 months | +5-7% | Standard short-term |
| 12-18 months | +8-10% | Medium-term |
| 18-24 months | +10-12% | Extended projects |
| 24-36 months | +15-18% | Long-term projects |

Material-Specific Volatility: - Structural Steel: ±20-25% (apply 2-3% per quarter) - Electrical Equipment: ±15-20% (apply 2-3% per quarter) - Concrete: ±5-10% (apply 1-2% per quarter) - HVAC Equipment: ±10-15% (apply 1.5-2.5% per quarter)

### Action Items for Future Projects

- Week 2: Determine project duration

- Week 2: Apply appropriate escalation factor based on duration

- Week 2: Add 2-3% contingency for material price risk

- Ongoing: Track quarterly material price indices

### Evidence from Advantech

- Project Duration: 21 months

- Applied Escalation: 7%

- Actual Escalation: 10-12%

- Lesson: Extended projects require higher escalation factors

## LESSON 3: CHANGE ORDER RISK MUST BE RESERVED

### What We Missed

We did not reserve contingency for anticipated change orders. The final account showed $4.3M in change orders (+6.0% of contract value).

### Impact

- Cost Impact: +$4.3M (40.8% of total variance - LARGEST SINGLE SOURCE)

- Original Contract: $71,200,000

- Change Orders: +$4,283,200

- Final Contract: $75,483,200

### Root Cause

- We assumed design was complete and scope was fixed

- We did not assess change order risk based on project complexity

- We did not reserve additional contingency beyond standard 12-13%

### Solution Implemented

New Change Order Risk Assessment:

| Risk Level | Change Order % | Trigger Conditions |
| --- | --- | --- |
| Low | 0-3% | Design complete, site conditions known, standard scope |
| Medium | 3-6% | Design 90% complete, some site unknowns, moderate complexity |
| High | 6-10% | Design 75% complete, significant unknowns, complex scope |
| Very High | 10%+ | Design preliminary, many unknowns, highly complex scope |

Recommendation: For complex projects, reserve 5-8% additional contingency for anticipated change orders beyond standard contingency.

### Action Items for Future Projects

- Week 2: Assess project complexity (single vs. multi-building, specialized systems)

- Week 2: Assess design completeness (% complete)

- Week 2: Assess scope definition (clear vs. undefined)

- Week 2: Reserve 3-8% additional contingency based on risk level

### Evidence from Advantech

- Project Complexity: HIGH (HQ + Warehouse, specialized systems)

- Design Completeness: 90%+ (design documents available)

- Change Orders: $4.3M (6.0% of contract)

- Lesson: Even well-designed complex projects experience significant change orders

## LESSON 4: SOFT COSTS MUST BE ADJUSTED FOR EXTENDED SCHEDULES

### What We Missed

We used a fixed 15% soft cost percentage without adjusting for the 21-month project duration.

### Impact

- Cost Impact: +$1.2M (11.4% of total variance)

- Applied Soft Cost %: 15%

- Actual Soft Cost %: 18-20%

- Difference: +2-5 percentage points

### Root Cause

- We applied standard 15% soft cost without considering project duration

- We did not account for extended project management costs

- We did not adjust for prolonged design coordination and permitting

### Solution Implemented

New Soft Cost Guidelines by Project Duration:

| Project Duration | Soft Cost % | Rationale |
| --- | --- | --- |
| 6-12 months | 15% | Standard short-term |
| 12-18 months | 15% | Standard |
| 18-24 months | 17-18% | Extended project management |
| 24+ months | 20-22% | Long-term project overhead |

Component Breakdown for 18-24 Month Projects: - Project Management: 5% (vs. 4% for standard) - Design Coordination: 2.5% (vs. 2% for standard) - Permits & Approvals: 2.5% (vs. 2% for standard) - Insurance & Bonds: 2% (unchanged) - Professional Services: 6% (unchanged) - Total: 17-18% (vs. 15% for standard)

### Action Items for Future Projects

- Week 2: Calculate project duration (months)

- Week 2: Apply appropriate soft cost percentage based on duration

- Week 2: Validate with project management team

- Ongoing: Track actual soft costs for continuous improvement

### Evidence from Advantech

- Project Duration: 21 months

- Applied Soft Cost %: 15%

- Actual Soft Cost %: ~18-20%

- Lesson: Extended schedules significantly increase soft costs

## LESSON 5: BASE COSTS MUST BE VALIDATED AGAINST DESIGN COMPLEXITY

### What We Missed

Our initial base costs were too low ($175/SF for HQ, $100/SF for AASC) without validating against design complexity.

### Impact

- Cost Impact: Contributed to 44.1% initial underestimation

- HQ Base Cost: Used $175/SF, should have been $210-225/SF

- AASC Base Cost: Used $100/SF, should have been $130-140/SF

### Root Cause

- We used standard warehouse/office base costs without adjusting for complexity

- We did not account for specialized systems (VRF HVAC, ESFR sprinklers, solar)

- We did not validate against design documents

### Solution Implemented

Updated Base Cost Guidelines:

Commercial Office Buildings (6+ Stories): - Base Cost/SF: $210-225 (vs. previous $175) - Rationale: Design complexity, full glass curtain wall, VRF HVAC, rooftop solar, ground improvement

High-Bay Warehouses (32+ ft Clear Height): - Base Cost/SF: $130-140 (vs. previous $100) - Rationale: High-bay steel structure, ESFR sprinkler system, solar integration, specialized systems

### Action Items for Future Projects

- Week 1: Review design documents for complexity indicators

- Week 1: Identify specialized systems (VRF, ESFR, solar, EV charging)

- Week 1: Adjust base costs accordingly

- Week 1: Validate with GC’s historical project data

### Evidence from Advantech

- HQ Design: 6-story, full glass curtain wall, VRF HVAC, rooftop solar

- AASC Design: 32-36 ft clear height, ESFR K25.2 sprinkler, 360 KW solar, 3 loading docks

- Actual Costs: Supported $210-225/SF (HQ) and $130-140/SF (AASC)

- Lesson: Specialized systems significantly increase base costs

## SUMMARY: UPDATED ESTIMATION PARAMETERS

### For Commercial Office Buildings (6+ Stories)

| Parameter | Previous | Updated | Rationale |
| --- | --- | --- | --- |
| Base Cost/SF | $175 | $210-225 | Design complexity, MEP systems |
| Labor Multiplier (CA) | 1.18x | 1.22x-1.28x | Confirm prevailing wage status |
| Material Escalation (18-24 mo) | +7% | +10-12% | Historical data from Advantech |
| Soft Cost % (18-24 mo) | 15% | 17-18% | Extended project management |
| Change Order Reserve | 0% | 5-8% | Complex multi-building projects |
| Total Contingency | 13% | 18-21% | Includes change order reserve |

### For High-Bay Warehouses (32+ ft Clear Height)

| Parameter | Previous | Updated | Rationale |
| --- | --- | --- | --- |
| Base Cost/SF | $100 | $130-140 | High-bay structure, specialized systems |
| Labor Multiplier (CA) | 1.18x | 1.18x-1.28x | Confirm prevailing wage status |
| Material Escalation (18-24 mo) | +7% | +10-12% | Historical data from Advantech |
| Soft Cost % (18-24 mo) | 15% | 17-18% | Extended project management |
| Change Order Reserve | 0% | 3-5% | Geotechnical unknowns |
| Total Contingency | 12% | 15-17% | Includes change order reserve |

## EXPECTED ACCURACY IMPROVEMENT

### Previous Performance

- Advantech Initial Estimate: $39.7M (44.1% underestimation)

- Advantech Final Estimate: $65.0M (13.8% underestimation)

- Target Accuracy: ±5%

### Expected Improvement with New Parameters

- With prevailing wage confirmation: -5% to -10% improvement

- With material escalation adjustment: -3% to -5% improvement

- With change order reserve: -5% to -8% improvement

- With soft cost adjustment: -2% to -3% improvement

- Expected new accuracy range: ±5-8% (vs. previous 13.8%)

## IMPLEMENTATION ROADMAP

### Phase 1: Immediate (This Week)

- ✓ Document 5 lessons learned

- ✓ Update ACCE-V3 system instruction with new Prevailing Wage Rule

- ✓ Update warehouse knowledge prompt with 4 new sections

- ✓ Create improved estimation model with updated parameters

### Phase 2: Short-term (Next 2 Weeks)

- Create healthcare knowledge prompt v2.0 (with lessons learned)

- Create commercial office knowledge prompt v1.0

- Update LAYER 1 calculation engine with material escalation & schedule impact models

- Test updated system with sample projects

### Phase 3: Medium-term (Next Month)

- Develop automated prevailing wage lookup by ZIP code

- Implement quarterly material escalation tracking

- Create change order risk assessment tool

- Establish feedback loop for continuous improvement

## RECOMMENDATIONS FOR FUTURE PROJECTS

### Week 1 - Initial Validation

- ☐ Confirm prevailing wage status (CRITICAL)

- ☐ Validate base costs against design complexity

- ☐ Confirm project location and regional factors

- ☐ Determine project duration

### Week 2 - Site Assessment & Risk Assessment

- ☐ Assess material escalation risk by duration

- ☐ Assess change order risk by complexity

- ☐ Adjust soft costs for schedule

- ☐ Validate with GC’s historical data

### Week 3 - Preliminary Estimate

- ☐ Execute Sanity Check Protocol

- ☐ Present estimate with all assumptions

- ☐ Get GC feedback on key uncertainties

- ☐ Refine based on feedback

### Week 4 - Detailed Refinement

- ☐ Present detailed BOQ

- ☐ Identify high-uncertainty items

- ☐ Get GC input on specific line items

- ☐ Finalize estimate

## CONCLUSION

The Advantech North America Campus project provided invaluable lessons for improving the ACCE-V3 estimation system. By implementing the five lessons learned and updating our estimation parameters, we can achieve our ±5% accuracy target for future projects.

Most Critical Takeaway: The three factors that had the largest impact on our underestimation were: 1. Not confirming prevailing wage status (21.9% of variance) 2. Underestimating material escalation (19.1% of variance) 3. Not reserving for change orders (40.8% of variance)

By addressing these three factors alone, we can improve accuracy by approximately 80% of the observed variance.

Document Prepared: January 31, 2026
System: ACCE-V3 Estimation Engine
Status: FINAL - Ready for Implementation